## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2019-09-02 | 2019-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2019-09-03 | 2019-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2019-09-03 | 2019-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2019-09-07 | 2019-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2019-09-09 | 2019-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2019-09-16 | 2019-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2019-09-16 | 2019-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2019-09-17 | 2019-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2019-09-22 | 2019-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2019-09-25 | 2019-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2019-09-25 | 2019-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2019-09-24 | 2019-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2019-10-02 | 2019-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
Project Management Plan - Version 1.1
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Rapid Application Development | Daniel Hee | 2019-11-05 | 2019-12-10 |  | 10% |  | SCOPE STATEMENT
AT RISK | TASK NAME | RESPONSIBLE | PRIORITY | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 2019-11-05 | 2019-11-12 | 8
| Gather client requirements | Daniel Hee, Tze Hon, Jayden Lee, Stuart Godwin | HIGH | 2019-11-05 | 2019-11-05 | 1 | Completed | Meeting minutes is provided
| Explain responsive & adaptive | Daniel Hee | MEDIUM | 2019-11-06 | 2019-11-06 | 1 | Completed | Definition and comparison of both are provided inside the report
| Decide responsive | Daniel Hee, Tze Hon, Jayden Lee | LOW | 2019-11-07 | 2019-11-07 | 1 | On-going
| Implementing types | Tze Hon | HIGH | 2019-11-08 | 2019-11-11 | 4 | On-going
| Testing | Jayden Lee | MEDIUM | 2019-11-12 | 2019-11-12 | 1 | On-going
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9